## Sheet1
Color Key:
Randy completed part of the work in Phase 2 as a subcontractor.
Additional layout Randy bid on, approved as additional work, and completed
Allocated to Cvent work (indicated in gold on Notion for Dec.).
Proposed additional WRI production work approved 9-8-23
WRI 2024 WEBSITE PHASE REPORT |  |  | Phase 1-2 |  |  | Phase 3 |  |  | Phase 4 |  |  | Phase 5
Phase 1 - Content | Budget |  |  | Actual | Delta |  | Actual | Delta |  | Actual | Delta |  | Actual | Delta
Initial discovery with client - additional discussions new WRS | 2 |  | Completed (no charge) |  | -2
PM time to discuss initial direction w/Erica/Randy | 1 |  | Completed | 3 | 2
Create a Style Guide for WRI (official palette, fonts and branding) | 2 |  | Completed | 2
Pull copy and edit for each component and page | 4 |  | Randy did most of this in the design phase (saved) | 1 | -3
Design and and tab icon (.ico file) | 0.5 |  |  |  | -0.5
Legal content pulled and edited as seems fit | 0.5 |  | This was done as a separate project. |  | -0.5
PM time to go through style guide, edits and legal copy | 2 |  | Completed | 2
Ond round of edits with client prior to build | 1 |  | Completed (with Erica and Brandon) | 1
PM time to offer basic meta info & social card image | 0.5 |  | Pushed to later in the process |  | -0.5
PM time to discuss database of customers | 1 |  | Decided to use CMS |  | -1
PM time to bring team up to speed on tailwind, etc - DONE | 1 |  | Completed (discussed with team & examples) | 1
Make client changes to Style Guide, legal and discuss images/elements | 1 |  | Randy handled this |  | -1
Simple wireframe mockup (pages, sections and form flow) | 2 |  | Decided on a full set as we had the hours | 10 | 9
Review of wireframe, functionality diagram & design elements | 0.5 |  | Completed |  | -0.5
Subtotal | 19 | 1615 |  | 20 | 1 |  | 20 |  |  | 20 |  |  | 20
Phase 2 - Site Concept Phase
Template layout and standard graphical page components | 1 |  | Randy - Gravital Paid from Project Budget | 1
Header component & navigation bar component - now multiple | 1.5 |  | Completed | 1.5
Tracks component with three color-coded blocks | 1 |  | Completed | 1
Home Design | 3 |  | Completed | 3
Rail Transit page - overview, speaker bios & topics (desk/mobile) | 2 |  | Completed | 2
Principles Course page - overview, speaker bios & topics (desk/mobile) | 2 |  | Completed | 2
Heavy Haul page - overview, speaker bios & topics (desk/mobile) | 2 |  | Completed | 2
Speaker card, resize and optimize speaker images (all speakers) | 2 |  | Completed | 2
Hotel and logistics page | 2 |  | Completed | 2
New WRS section (group of companies) | 2 |  | Completed | 2
Sponsor images optimize | 1 |  | Completed | 1
Archive page template (for future event archival interface) | 2 |  | Completed | 2
FAQ page | 1 |  | Completed | 1
Info Zone page - Make more significate (a main feature) | 2 |  | Completed | 2
Simple confirmation and thank you page | 1 |  | Completed | 1
OTS image carousel/hero and 6-12 images optimized | 5 |  | Completed | 5
Footer component | 1 |  | Completed | 1
PM multiple internal and client review meetings | 2 |  | Completed | 2
Two rounds of edits with client approval prior to build | 4 |  | Completed | 4
Subtotal | 37.5 | 3187.5 |  | 37.5 |  |  | 37.5 |  |  | 37.5 |  |  | 37.5
Additional page designs in XD for graphics | 21.25 | 2900 | Randy - Gravital Paid
Phase 3 - Development Phase
App and repo setup | 1 |  | Completed |  |  |  | 1
Supporting library setup | 1 |  | Completed |  |  |  | 1
Set up client account for CDN hosting | 1 |  | Completed |  |  |  | 1
Meta tags, card (basic seo/social) setup | 1 |  | Completed |  |  |  | 1
CMS Setup with all content sections | 16 |  | Completed (but only connected speaker pages) |  |  |  | 8 | -8
Determining logic for content types for multiple conferences | 4 |  | No longer needed |  |  |  | 0 | -4
CMS Setup for active and archival stages of track content (and access pg) | 8 |  | No longer needed |  |  |  | 0 | -8
Layout template build | 3 |  | Completed |  |  |  | 3
Navigation component build | 2 |  | Completed |  |  |  | 2
Footer component build w/CMS api | 3 |  | Completed |  |  |  | 3
Header component build w/CMS api | 3 |  | Completed |  |  |  | 3
News/updates section build w/CMS api (WRI appouncements) | 3 |  | Completed |  |  |  | 3
Home page build (with sponsor sections w/CMS api) | 4 |  | Completed |  |  |  | 3 | 1
Rail Transit page/components build w/CMS api | 4 |  | Completed |  |  |  | 11.25 | 6.25 | Request to change content layout top (all 3)
Principles Course page/component build w/CMS api | 4 |  | Completed |  |  |  | 9.25 | 5.25
Heavy Haul page/components build w/CMS api | 4 |  | Completed |  |  |  | 11.75 | 7.75
Info Zone page/componenet build w/CMS api | 4 |  | Completed |  |  |  | 4
Speaker cards and component build w/CMS api (and all speaker data) | 2 |  | Now a page (but combined) - Completed |  |  |  | 2
Bios and Abstract Page Rail Transit (and CMS system) |  |  | Completed |  |  |  | 12.5 | 12.5 | This was for integrating Storyblok CMS
Logistics page and hotel links and build page and buttons (_blank link) | 1 |  | Completed |  |  |  | 1
Simple registration form with multiple tracks and on-site & virtual | 16 |  | Allocated to Cvent hours on 12-12-23 |  |  |  | 16 |  |  | 2
Basic thank you and 404 pages from template | 0.5 |  | Allocated to Cvent hours on 12-12-23 |  |  |  | 0.5
Making the updates to the Stripe registration for WRI | 0 |  | N/C
Modifying the existing registration checkout page | 1 |  | Allocated to Cvent hours on 12-12-23 |  |  |  | 1
Connect registration form with Firebase or similar (customer db) | 1 |  | Allocated to Cvent hours on 12-12-23 |  |  |  | 1
Work with client on registration options (different pricing) | 0.5 |  | Completed |  |  |  | 6 | 5.5 | Added additional pricing tables
Configure hooks to send email confirmation and links to edit | 4 |  | Allocated to Cvent hours on 12-12-23 |  |  |  | 4
Stripe Gateway configuration and test | 1 | 1 | Allocated to Cvent hours on 12-12-23 |  |  |  | 1
Minimum legal: privacy and cookie copy/elements | 1.5 | 1.5 | Completed |  |  |  | 1.5 |  | Used the time for terms
Cookie popup to keep site GDRP and California compliant | 0 |  | Handled as a separate project.
Review dashboard (simple - no custom config) | 1 | 1 | Allocated to Cvent hours on 12-12-23 |  |  |  | 1
Form test and debug allowance | 3 | 3 | Allocated to Cvent hours on 12-12-23 |  |  |  | 3
Gateway test and debug allowance | 0 |  | N/C
Built-in PM time for questions, email and general work | 3 | 3 | Completed |  |  |  | 3
Subtotal | 101.5 | 8627.5 |  |  |  |  | 118.75 |  |  | 118.75 |  |  | 118.75
Phase 3 Additions to WRI site design
Previous conference overview cards (3) | 1.25 |  | These were approved as part of Randy's design. |  |  |  | 1.25
Info Zone/Expo Zone Cards | 1 |  | Completed |  |  |  | 1 |  | Saved time pulling code from WRS project
Expo Zone page/component build w/CMS api | 4 |  | Not needed |  |  |  |  | -4
Interface Journal component w/RSS feed | 4 |  | Not needed |  |  |  |  | -4
Sponsor page with various tiers build w/CMS/graphics api | 4 |  | Completed |  |  |  | 4
Hotel Page | 3 |  | Full Page Not needed |  |  |  |  | -3
Worth Award and possible academic scholarship page | 3 |  | Never heard back on this one (legal issues?) |  |  |  |  | -3
Subtotal | 20.25 | 1721.25 |  |  |  |  | 6.25 |  |  | 6.25 |  |  | 6.25
Phase 4 - Revisions Phase
PM time to present, walkthrough, questions, edits. | 2 |  | Completed | [6 empty] | 2
All written content final edit allowance | 2 |  | Completed | [6 empty] | 9.25 | 7.25
Forms (incl. thank you page) final polish allowance | 1 |  | Not needed
Image change allowance | 1 |  | Completed | [6 empty] | 6 | 5 | Went ahead and resized all sponsor logos
Misc. 'polish' allowance | 1 |  | Completed | [6 empty] | 4.5 | 3.5 | I went through the entire site fixing layout issues, etc.
Produce 1-page PDF instructions to access dashboard | 1.5 |  | Completed | [6 empty] | 1.5 |  | This I put toward Cvent Reports and Dashboard
PM time for training on accessing dashboard reports | 0.5 |  | Completed | [6 empty] | 0.5 |  | Shared reports/dashboard instructions w/ team
Produce multiple-page PDF instructions for CMS editing | 8 |  | Only needed a few slides | [6 empty] | 3
CMS editing video walkthrough and 2 1-hour sessions of Zoom training | 4 |  | Only needed a short video | [6 empty] | 0.5
Subtotal | 21 | 1785 | [7 empty] | 27.25 |  |  | 5.5
Phase 5 - Site Launch and Final Production Test Phase
Set up hooks to repo for auto builds | 0.5 | 0.5 | Completed | [9 empty] | 0.5
Allowance for any additional configure and SSL | 0.5 | 0.5 | Completed | [9 empty] | 0.5
Google Analytics or Plausible simple setup (no GTM) | 0.5 | 0.5 | Completed | [9 empty] | 0.5
Full content/component testing and basic polishing | 0.5 | 0.5 | Completed | [9 empty] | 0.5
Firebase or similar testing on production & debug all. | 1 |  | Not needed
Lighthouse test & report review | 0.25 | 0.25 | Completed | [9 empty] | 0.25
PM time to present, walkthrough & signoff | 1 | 0 | Steve donated. See note >> | [9 empty] | 0 |  | This is handled in my online report (on my dime).
Allowance for minor optimization & any final tweaks | 1 | 3.5 | Completed | [9 empty] | 3.5
Subtotal | 5.25 | 446.25 | [10 empty] | 5.75
|  |  |  | Phase 1 & 2 |  |  | Phase 3 |  |  | Phase 4 |  |  | Phase 5
Total | 204.5 |  |  | 57.5 | 57.5 | hrs. to date | 125 | 182.5 | hrs. to date | 27.25 | 209.75 | hrs. to date | 5.75 | 215.5 | hrs. to date
Hourly Rate | 85
Project Budget (updated later with approved funds for Randy) | 17382.5 | 20282.5 | Final Project Fee: $20,117.50 (215.5 hrs + $1,800)
Summary of payments/invoices | Amount | Invoiced | Paid
Deposit for 10% of project (estimated hours) | 1472 | 2023-03-02 | 3/9/23 (invoice 00030)
Deposit adjustment for additional WRS hours | 227.37 | 2023-08-17 | 9/1/2023 (invoice 00044)
Phase 2 at budget | 3123.75 | 2023-08-17 | 9/1/2023 (invoice 00044)
Phase 2 balance | 63.75 | 2023-09-11 | 9/26/2023 (invoice 00047)
Additional P2 work to pay Randy | 1800 | 2023-09-11 | 9/26/2023 (invoice 00047)
Phase 3 - first half of estimated hours (101.5 + 20.25 = 121.75) | 5174.38 | 2023-09-11 | 9/26/2023 (invoice 00047)
Made a 1.0 correction but total was accurate so no invoice change ^
Note that we agreed to split P3 into two invoices in early Sept.
Final Invoice | 8256.25 | 2024-02-22
Total Invoiced | 20117.5
Summary as of 12-12-23 | Budget | Delta
Phase 1 | 19 | 1
Phase 2 | 37.5 | 0
Phase 2 hours for Randy to finish layouts (approved at $1,800 per Gordon)
Phase 3 | 121.75 | 3.25
Randy's approved additional Phase 3 sections/pages | 20.25 | 0
Phase 4 | 21 | 6.25
Phase 5 | 5.25 | 0.5
| 204.5 | 11 | 5.38%
NOTE: Additional time will be required to implement Authorize.net
Assumptions at time of bidding project:
Basic analytics and one monthly auto report
No search capability but option to add to archives later
Free CDN hosting based on free tier which should be adequate
Assumes provided URL and access to point to host
Basic Google Lighthouse optimization